## Sheet1
Week | Task | Completed on time in the assigned week | Completed tasks until now | Completed task whole project
|  | 100% | 100% | 1.667%
Type 1 if true, 0 if false
1 | Attend lecture | 1 | 1
1 | Attend lab
1 | Join a group
1 | Plan weekly group meetings (fixed times)
1 | Set up group communication (e.g., Whatsapp group)
1 | Read overview file on Nestor
1 | Discuss project ideas in group
1 | Discuss possible experts in group
1 | Discuss tech options in group (pre-existing system, from scratch?)
1 | Submit sketch of project idea
1 | Submit sketch of expert
2 | Attend lecture
2 | Attend lab
2 | Attend group meeting
2 | Do knowledge acquisition exercise (part 1)
2 | Finalize project idea and expert
2 | Plan meetings with expert (all)
2 | Implement hello world
2 | Submit hello world
2 | Submit final project idea and expert
3 | Attend lecture
3 | Attend lab
3 | Attend group meeting
3 | Do knowledge acquisition exercise (part 1)
3 | Submit knowledge acquisition exercise
3 | Design initial problem solving model (including choice of inference: backward, forward chaining)
3 | Design initial domain model
3 | Design initial rule model
3 | Write project plan
3 | Implement initial prototype
3 | Submit project plan
4 | Attend lecture
4 | Attend lab
4 | Attend group meeting
4 | Finalize complete prototype
4 | Submit complete prototype
5 | (No lectures from now on)
5 | Attend lab
5 | Attend group meeting
5 | Implement system
5 | Write initial project report (aka system report)
5 | Submit initial project report (aka system report)
6 | Attend feedback session (groupwise)
6 | Attend group meeting
6 | Implement system
6 | Write final project report
7 | Attend lab
7 | Attend group meeting
7 | Implement system
7 | Write final project report
7 | Evaluate system with expert
8 | Attend lab
8 | Attend group meeting
8 | Finalize system
8 | Finalize report
8 | Submit final system
8 | Submit final report
9 | Prepare project presentation
9 | Present project
9 | Submit project presentation